## Japanese (hidden)
現場視察時安全管理チェックリスト
案件名： |  |  | 日付： 年 月 日 |  |  | 時間： | ～
視察場所： |  |  | ｽｷｰﾑ： |  |  | 天候：
視察者： |  |  | 同行者：
項目 | 視察のポイント
服装 安全具 | 下請業者作業員の服装、安全具装備は下請業者に委ねられているケースが多い。作業によって安全具を着用するのではなく、少なくともヘルメット、服、靴は現場にいる限り装着する。安全具の着用状況の悪さは安全管理に対する意識の低さを示し、事故発生のリスクも高いといえる。
第三者対策 | 工事関係者の家族が現場に来ていたり、物売りが現場内に入ってきたり、子供が物珍しさもあって場内に入ったり、第三者の侵入に対して管理が甘い。仮囲いは「侵入禁止を示す」ものではなく、「侵入を阻止する」もの。道路の工事現場では、反射板や照明など夜間の視認性についても確認が必要。夜間の転落事故や衝突事故が多い。
墜落・落下 防止 | 現地作業員は身軽で慣れていても、日本人を含む監督員がすべての工事箇所に安全にアクセスできなければならない。一般に「2～3mが最も危険な高さ」と言われている。転落・落下防止策が疎かになりがちだが、重傷事故につながりやすい。この高さでの対策の有無は安全管理良否の目安。
重機作業 | 一般に途上国の現場で使用されている重機は老朽化し、整備不良のものが多い。安全装置の作動確認が極めて重要。少ない機材をフルに使用するケース(目的外使用）も多い。重機オペレータ、トラック運転手の過労が事故を招くケースも多い(スピードの出しすぎ、居眠り運転など）。小さな現場では、重機のメカニックを配置せず、オペレータに整備をさせるケースも多い。整備コストがかけられず、整備不良のまま使用している機械が多い。オペレータの資格、経験年数(熟練度）は安全作業の必要条件。
安全標識 安全活動 | 末端の作業者が「安全作業」、「事故防止」を意識し継続させる仕組が設けられているか？ 比較的大手の業者ではこれらの安全対策が定型化されているが、形骸化しているケースも多い。これらの活動を「実施した記録」ではなく、「改善事項の記録」に着目すべき。
整理整頓 規律 | 「きれいな現場」は施工品質がよく、事故も少ない。素人目に見て「きたない」現場は事故リスクが高いとみてよい。特に作業動線（足場上含む）に工具や資材が置かれていないか、作業を行っていない場所に工具、資材が放置されていないかをチェック。廃棄物の分別処理義務はなくても、種類ごとに整理されていれば「よい現場」といえる。
わからないことは恥ずかしがらずに尋ねよう。
項目 | チェックポイント |  | 結果 |  |  | 気付きの点
服装・安全具 | □ | ヘルメット、靴、長袖、長ズボン、蛍光ベストの着用 | □ 適 | □ 不適 | □ 該当なし
| □ | 危険作業時の手袋、保護メガネ、マスク等の着用 | □ 適 | □ 不適 | □ 該当なし
第三者対策 | □ | 部外者侵入予防のための仮囲いは設置されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 仮囲いの状態は良好か（開口部はないか、倒れてないか？）？ | □ 適 | □ 不適 | □ 該当なし
| □ | 場内に部外者が不必要に立ち入っていないか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 出入り口へ警備員が配置され、出入りが管理されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 工事現場外に工事用資機材が置かれていないか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 【道路】誘導標識等の夜間の視認性は十分か？ | □ 適 | □ 不適 | □ 該当なし
| □ | 【道路】一般通行人用の通路は適切に確保されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 【道路】誘導員は配置され、役目を果たしているか？ | □ 適 | □ 不適 | □ 該当なし
項目 | チェックポイント |  | 結果 |  |  | 気付きの点
墜落・落下 防止 | □ | 足場フレームはきちんと固定されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 足場板は固定されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 足場板の幅は十分か、板は枠に固定されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 足場に手摺りは設けられているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 足場へ上る仮設階段は階段としてふさわしいか状態か？ | □ 適 | □ 不適 | □ 該当なし
| □ | 開口部の周囲には墜落防止柵が設けられているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 高所作業時に安全帯（命綱）は使用されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 安全帯（命綱）の固定場所は確保されているか？ | □ 適 | □ 不適 | □ 該当なし
重機作業 | □ | 重機周りには立ち入り禁止区域が明示され、その中に人はいないか？監視員は配置されているか？（クレーン等） | □ 適 | □ 不適 | □ 該当なし
| □ | クレーンによる一点吊、フックはずれ止めの欠落、ワイヤーの部分断裂等はないか？ | □ 適 | □ 不適 | □ 該当なし
| □ | バックランプ、バックホーンは作動するか？後進スピードは速すぎないか？誘導員は配置されているか？（ローラー等） | □ 適 | □ 不適 | □ 該当なし
| □ | 用途外使用はないか（バックホウでの吊作業など） | □ 適 | □ 不適 | □ 該当なし
| □ | オペレーターは有資格者/熟練者か？ | □ 適 | □ 不適 | □ 該当なし
安全標識 安全活動 | □ | 現地語の安全注意喚起看板は設置されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 安全教育は実施されているか？（新規作業員、運転手等） | □ 適 | □ 不適 | □ 該当なし
| □ | 安全作業マニュアルはあるか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 朝礼、安全パトロール、安全大会等は開催されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 施工会社の安全管理要員は配置されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 安全パトロールの結果・改善策等記録に残されているか？ | □ 適 | □ 不適 | □ 該当なし
整理整頓 規律 | □ | 現場は整理整頓されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 場内には通路は確保されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 作業場、資材置き場は決められているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 喫煙場所は設けられているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 酔っぱらいや、飲食・喫煙しながら作業している者はいないか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 作業中に携帯電話を操作している者はいないか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 可燃物は鍵のかかる倉庫に保管されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 廃棄物置き場は設けられ、分別されているか？ | □ 適 | □ 不適 | □ 該当なし
仮設電気 | □ | 高圧線の近傍でのクレーン作業時、ブームが高圧線に触れないよう専任の監視・指示員が配置されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 遮断器(ブレーカー）は雨水が侵入しないような構造の仮設分電盤内に設置されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 仮設分電盤内に漏電遮断器が設置されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 電気器具からはアースが取られているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 地面上の電線は保護されているか？ | □ 適 | □ 不適 | □ 該当なし
| □ | 電線の接続（延長）箇所は水に濡れても安全な状態か？ | □ 適 | □ 不適 | □ 該当なし
その他気付いた点

## DPIO 05. ANEXO 4
REGISTRO DE ENTREGA DE INVITACIONES A LA SOCIALIZACION DEL PROYECTO A LOS ACTORES SOCIALES DEL ÁREA DE INFLUENCIA DIRECTA Y BENEFICIARIOS |  |  |  |  | FECHA: 15/10/2025
VERSIÓN: 0
DPIO 05. ANEXO 4
Nombre del proyecto
Nombre de la persona que entrega las invitaciones |  |  | Etapa del proyecto
Nro. | NOMBRE | ACTOR | REPRESENTACION | PERTENENCIA | FIRMA RECEPCION
1
2
3
4
5
6
7
8
9
10
11
12
13
FOTOGRAFIAS DE LAS ENTREGAS FECHADAS Y GEOREFERENCIADAS

## English (Modified) (hidden)
Check list for safety on construction site (GENBA)
Project: |  |  | Date: |  |  | Time | ～
Place: |  |  | Scheme: |  |  | Weather
Visitor's name: |  |  | accompanied by:
item | point to check
5S | 5S comes first
clothes, PPE* | Usage of helmet, clothes and shoes is minimum requirement on site. We may say that these usage is the mirror of contractor's awareness level on safty. Accidents risk, therefore, seems high, if the usage of PPE is poor.
third parties accidents | If temporary fence and gate are not under proper control, third parties such as visitorｓ having nothing to do with the work, street vendors and curious children, may enter into the site. Therefore, purpose of temporary fence is not to prohibit third parties from getting into the site, but to block them. And for road construction, visibility of reflective traffic sign boards and lighting at night should be confirmed to reduce the traffic accident risk at night.
falling accidents | All the workers, supervisors and japanese staff have to access safely to any construction spot including high place. It is said that work on 2 to 3m high from ground/floor level is the most dangerous. As falling accidents often results in serious accidents, falling prevention measures on this hight may reflect over all safety management of contractor.
heavy machinaries accidents | Generally heavy machinaries used in developping countries construction sites are old and not well maintained. And it is sometimes observed that they are used other than original pursose. In small scale sites, operators often have to be in charge of their maintenance instead of mechanics due to the cost restriction, which sometimes causes their poor maintenance. Operators license, their experience are also important factor for safe work. In addition, there are many cases that accidents are caused by overwork of operators and drivers.
safety sign board, safety activities | Is there any mechanism where all workers can be continuously aware of safety and accident prevention? Usually large scale contractors have such mechanism but sometimes it becomes a dead letter. We should look at not only activities record but rectified record when rectification is instructed upon safety patrol etc.
sorting, tidiness, discipline | In clean, sorted and well organised site, there is very few accidents and quality of work is relatively high. Conversely in dirty site such that tools and materials are observed scattered on the ground, accident risk is high. We can call "Well managed site", if waste is sorted despite no obligation. | [9 empty] | A | Good
*PPE：Personal Protective Equipment such as helmet, gloves, protective eye glass etc. | [10 empty] | B | Average
[11 empty] | C | Poor
Check points | [10 empty] | N/A
item | to check |  | Result |  |  | Remarks |  | SEIRI | SEITON | SEIKETSU | SEISO | SHITSUKE
clothes, PPE | □ | Workers wear helmet, shoes, clothes with long sleeves, trousers and reflective jacket. | □ good | □ not good | □ N/A
| □ | Workers wear gloves, goggles and mask while at work in danger. | □ good | □ not good | □ N/A
avoid third parties accidents | □ | Temporary fence has been properly set up around site to keep third parties off. | □ good | □ not good | □ N/A
| □ | No defects of temporary fence are found.(no hole, no partial collapse etc.) | □ good | □ not good | □ N/A
| □ | No third parties are found in the site without permission. | □ good | □ not good | □ N/A
| □ | Entrance gate is controlled by authrised gate keeper. | □ good | □ not good | □ N/A
| □ | No construction materials and tools are kept outside the site. | □ good | □ not good | □ N/A
| □ | 【road】Traffic sign boards are visible enough even at night. | □ good | □ not good | □ N/A
| □ | 【road】Passage ways for third parties is properly secured. | □ good | □ not good | □ N/A
| □ | 【road】Flagman for traffic control is stationed and performs his duty. | □ good | □ not good | □ N/A
falling accidents | □ | Scaffolding is properly tied and fixed. | □ good | □ not good | □ N/A
| □ | Scaffolding board is tightly fixed. | □ good | □ not good | □ N/A
| □ | Scaffolding board is wide enough. | □ good | □ not good | □ N/A
| □ | Handrail is installed in high place. | □ good | □ not good | □ N/A
| □ | Proper temporary stair is installed to working platform in high place. | □ good | □ not good | □ N/A
| □ | Guardrail is set up around hole to prevent falling accident. | □ good | □ not good | □ N/A
| □ | Safety harness is used at work in high place. | □ good | □ not good | □ N/A
| □ | Safety harness rope is properly hooked. | □ good | □ not good | □ N/A
heavy machinaries accidents | □ | "Keep off" area is designated around working heavy machinaries and watchman is stationed(crane, back hoe etc.). The instruction is properly observed. | □ good | □ not good | □ N/A
| □ | Cargo should not be slung by one rope. Hook has rope come-off prevention implement. Sling rope is in sound condition. | □ good | □ not good | □ N/A
| □ | Heavy machinaries working on road has reverse warning lamp, reverse warning horn. They don't move reversely too fast. Flagman is stationed for them. | □ good | □ not good | □ N/A
| □ | Machinaries are not used other than original purpose. | □ good | □ not good | □ N/A
| □ | Machine operators have appropriate lisence/lot of experience. | □ good | □ not good | □ N/A
point | to check |  | Result |  |  | Remarks
safety sign board, safety activities | □ | Safety sign boards written in local language are set up to call workers attention. | □ good | □ not good | □ N/A
| □ | Safety instruction is carried out(instruction for new workers, drivers etc.) | □ good | □ not good | □ N/A
| □ | Safety manual is prepared. | □ good | □ not good | □ N/A
| □ | Daily morning assembly, monthly safety assembly and regular safety patrol are held. | □ good | □ not good | □ N/A
| □ | Contractor appoints safety officer. | □ good | □ not good | □ N/A
| □ | Result of safety patrol and taken counter measures are properly recorded. | □ good | □ not good | □ N/A
sorting, tidiness, discipline | □ | Site is clean and in orderly condition. | □ good | □ not good | □ N/A
| □ | Passage ways for workers are secured. These are not blocked by machinaries and materials. | □ good | □ not good | □ N/A
| □ | Workshop and material storage space has been designated in the site. | □ good | □ not good | □ N/A
| □ | No smoking workers outside designated smoking area. | □ good | □ not good | □ N/A
| □ | No drunken, drinking and eating workers found in site. | □ good | □ not good | □ N/A
| □ | No workers using mobile phone while working. | □ good | □ not good | □ N/A
| □ | Combustibles are properly kept in locked storage. | □ good | □ not good | □ N/A
| □ | Site waste is sorted and kept in designated area. | □ good | □ not good | □ N/A
temporary power | □ | Operating instructor for slinging work is in duty while cranes etc. being used in proximity of aerial high voltage line. | □ good | □ not good | □ N/A
| □ | Circuit breakers etc. are housed in rainproof temporary distribution board. | □ good | □ not good | □ N/A
| □ | ELB(Earth Leakage Breaker) is installed for temporary power. | □ good | □ not good | □ N/A
| □ | Electric driven tools are properly earthed. | □ good | □ not good | □ N/A
| □ | Electric wires on the ground are protected. | □ good | □ not good | □ N/A
| □ | Electric wires are connected(extended) in safe manner against electric leakage even if they get wet. | □ good | □ not good | □ N/A
Any other comment